## Table1
# | Risk | Likelihood | Impact | Mitigation
R-1 | State drift between dashboard and backend orchestrator (UI shows wrong stage/status) | High | High | Backend as single source of truth; event/stream-driven sync with periodic reconciliation; never derive state from optimistic UI alone.
R-2 | Interactive-input parity gap — a pipeline prompt has no UI representation, blocking runs | High | High | Build F-11 coverage checklist against every pipeline feature; generic fallback dialog renderer for unknown input types; gate releases on coverage audit.
R-3 | Long-running runs vs. deployed host limits (e.g., serverless timeouts on public hosts) | High | High | Keep orchestration long-running in backend, not the dashboard host; dashboard holds a streaming client connection only; document split topology where backend is always-on.
R-4 | Streaming/log volume and reconnection — dropped streams, unbounded logs | Medium | High | Resumable streaming with cursor/offset, backpressure, buffered history, retention policy, reconnect with backoff.
R-5 | Security exposure via public deployment — anyone reaching the dashboard could trigger runs or see artifacts/code | High | High | Mandatory authentication and access control before public deployment; scoped operator vs. viewer roles; secrets never stored in UI; audit all control actions.
R-6 | API key / provider credential handling for tiers | Medium | High | Store credentials server-side only, never returned to client; masked inputs; per-provider scoping; rotation support.
R-7 | Auto mode runaway cost — unattended runs burn tokens across many projects | Medium | High | Per-project and portfolio budget caps; cost tracking (F-22) with hard stop thresholds; approval gates for over-budget actions.
R-8 | Voice privacy and accidental activation — always-listening perception, wake-word false positives | Medium | Medium | Voice off by default; active only when enabled AND dashboard focused/open; persistent listening indicator, easy mute, no audio retention beyond processing; documented privacy behavior.
R-9 | Mobile scope creep — mobile app attempts full-dashboard parity and stalls delivery | High | Medium | Fix an explicit mobile workflow subset (F-21) as the contract; explicitly defer non-mobile-feasible flows to web.
R-10 | Multi-project concurrency conflicts — shared artifacts, shared backend resources, interleaved state | Medium | High | Per-project isolated workspaces; concurrency limits and queueing; per-project locks on artifacts and config; clear resource/quota reporting.
R-11 | UI/feature drift as pipeline evolves — new pipeline features ship without dashboard coverage | Medium | High | Coverage checklist enforced as an ongoing requirement; pipeline feature checklist surfaced in UI; version/contract check between dashboard and backend.
R-12 | Chat/voice companion acting on wrong project or taking destructive action | Medium | High | Explicit target resolution and confirmation for destructive actions (stop, delete, re-run); read-only by default; disambiguation prompt when target is ambiguous.
R-13 | Persistence/data loss — losing run history, configs, tier definitions | Low | High | Durable store with backups/export; configs and tier library exportable/importable; audit trail append-only.
R-14 | API surface duplication — building everything new instead of reusing pipeline APIs, fragmenting sources of truth | Medium | Medium | Explicit reuse-vs-extend decision (F-17) documented before implementation; only dashboard-specific endpoints added; shared schema/contract.
R-15 | Test framework becomes a side product and is under-maintained | Medium | Medium | Scope it to dashboard-relevant test types and pipeline integration; integrate results/issues into the project view rather than building a standalone QA suite.
R-16 | Accessibility/theme quality regressions from rapid UI build-out | Medium | Medium | Shared design system (F-15) as the only path for new UI; accessibility checks in the definition of done.
R-17 | Backend unavailability / partial outage leaves dashboard blank | Medium | Medium | Connection health + reconnect (F-32); cached read-only last-known state; clear degraded-mode messaging.
R-18 | Human-input bottleneck — many concurrent runs each waiting on operator decisions | Medium | Medium | Consolidated "needs me" inbox across projects; notifications; auto mode for runs that need no input.